## Project Data
Project Name | AI Driven Testing
Online team meeting | https://fau.zoom.us/j/69553438847?pwd=VHGm0oOZ2KvPbbhrGsmX83d4rAuuaT.1
Production system (if any) | ...
Test system (if any) | ...
GitHub repository | https://github.com/amosproj/amos2025ss04-ai-driven-testing
GitHub feature board | https://github.com/orgs/amosproj/projects/82/views/2
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/86/views/1
Planning Poker Link | https://pokerplanning.org/room/05e2b4ba-b452-4c29-8ba0-e9ae23005ce0
Team T-shirt (white) | https://www.shirtinator.ch/s/gyMoSd27QOSllB0wUYQ7XA
Team T-shirt (black) | https://www.shirtinator.ch/s/-GuNOvW5Q2qjHFDZrYILpA
black link again since it didnt work for some | https://www.shirtinator.ch/t-shirts/gestalten/t-shirt-bedrucken#/load/share/f86b8d3a-f5b9-436a-a31c-50d9ad820ba4
Additional materials | ...
Team maling list | oss-amos-proj4@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Brüggemann | Jonas | JonasBrue | jonas.brueggemann@campus.tu-berlin.de
Clicqué | Lennard | OlafVanHuusen | lennard.clicque@fau.de
Hasse | Lisabeth | PeppermintCoding123 | lisabeth.hasse@fau.de
Heidkamp | Tessa | theidkamp | tessa.v.heidkamp@campus.tu-berlin.de
Krug | Maximilian | HaruspexSan | maximilian.krug@fau.de
Lang | Felix | xilef45 | felix.l.lang@fau.de
Lorenz | Alexander | Hydraneut | alexander.lorenz@fau.de
Parameswaran | Biranavan | Biranavan-Parameswaran | parameswaran@campus.tu-berlin.de
Takale | Aditi Vishwas | adititakale01 | adititakale01@gmail.com
Alsultan | Moaiad | Moaiadsu | m.alhmadhalsultan@campus.tu-berlin.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | First-Level-Support :) | Comment
1 | 2025-04-16 | both | both | all other | none | Felix | Felix
2 | 2025-04-23 | both | Max | all other | Max | Felix | Felix
3 | 2025-04-30 | Max | Alex | all other | Alex | Felix | Felix
4 | 2025-05-07 | Alex | Max | all other | Jonas | Felix | Felix | Build process review
5 | 2025-05-14 | Max | Alex | all other | Lennard | Felix | Felix
6 | 2025-05-21 | Alex | Max | all other | Lisabeth | Felix | Felix
7 | 2025-05-28 | Max | Alex | all other | Tessa | Felix | Felix | Mid-term due
8 | 2025-06-04 | Alex | Max | all other | Max | Felix | Felix
9 | 2025-06-11 | Max | Alex | all other | Alexander | Felix | Felix
10 | 2025-06-18 | Alex | Max | all other | Biranavan | Felix | Felix
11 | 2025-06-25 | Max | Alex | all other | Aditi Vishwas | Felix | Felix
12 | 2025-07-02 | Alex | Max | all other | Moaiad | Felix | Felix
13 | 2025-07-09 | Max | Alex | all other | Jonas | Felix | Felix
14 | 2025-07-16 |  |  | all other | Lennard | Felix | Felix | Demo day!
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Interpersonal relationship objectives: “To foster an atmosphere of mutual respect and learning, creating a team-spirit”
Main goal is to create a satisfiying project that makes Us, the IP(Industry Partner) and open-source community happy
Meeting norms | Documentation in english and meeting language in German
Start on time
Be Polite
Purpose: Clearly define the goal of the meeting. Preparation: Ensure all participants are well-informed and ready to contribute. Participation: Encourage active engagement from all attendees. Process: Organize the meeting structure and agenda effectively. Progress: Monitor the meeting's progress and ensure it stays on track.
Working norms | Leave the code better than you found it (The Boy Scout Rule)
Keep it Simple, Stupid (KISS)
Coordination norms | Felix will do the retros + keeping track of meetings
Alex and Max will take care of the assignments (Backlog Items)
Communication norms | We check Discord at least every day
Consideration norms | Communicate Conflict in Team-Meeting. Help from Felix or Jovana to solve conflicts.
Respect, active listening, tolerance
Cont. improvement norms | Experimentation spirit and feedback culture
Burn-Down charts as process tracking
Rewards | Appreciation and praise
Sanctions | Wear the ducky tie
Post a cute/funny pic of a pet (or similar)
Signatures
Scrum Master | Felix Lang
Product owner | Maximilian Krug
Product owner | Alexander Lorenz
Software developer | Mohammad Moaiad Alhamdh Alsultan (Moaiad Alsultan)
Software developer | Jonas Brüggemann
Software developer | Lennard Clicqué
Software developer | Biranavan Parameswaran (Biri)
Software developer | Lisabeth Hasse
Software developer | Tessa Heidkamp
Software developer | Aditi Vishwas Takale

## Product Goal
Product Vision | Project Mission
Product Vision We are transforming the landscape of software testing through intelligent, AI-powered automation. Our vision is a future where testing is no longer a bottleneck but a seamless, continuous, and reliable part of the development process. By empowering developers and testers with AI tools that autonomously generate and maintain test cases, we free them from generating the same test cases over and over to instead focus on creative problem-solving and strategic innovation. Our solution supports a future of scalable, secure, and locally controlled quality assurance, driving the next evolution in software development. We invision the role of the programmer to become a curator and innovator of AI generated Code. | Product Mission Deliver a minimum viable product (MVP) of an AI-powered test generation assistant that interacts effectively with real-world software projects. This includes laying the empirical and research groundwork for the idea. From this research we will conclude a MVP, that can analyze simple Python and C++ programs and produce corresponding test cases. Operated through a user-friendly chat interface. The MVP will showcase initial integration with widely used open-source testing frameworks such as Robot Framework, proving the viability of AI-assisted test automation in practical, everyday development environments.

## Product Glossary
Term | Definition
LLM | Large language model
LLM Input | User Input into the LLM
LLM Output | Response of the LLM to the Input
LLM System Prompt | System message sent (this is different from the LLM Input)
Temperature | gradient how "creative" the LLM behaves
Interface Script/ LLM factory | Backbone script of the project to start, end and use the LLM containers
Container | Docker container, (not kaniko os something else)
IP | Industry Partner
Sprint | agile (Amos) sprint with a duration of 2 weeks
CI | GitHub workflows as Continuouse Integration assistent
Wiki | Documentation in the Github repos wiki (not Wikipedia)
Laptop | Personal device to run the code (nothing fancy standard device) TODO add specs
API | Application Programming Interface
UI | User Interface
UX | User Experience
Database | Organized collection of data
Cloud Computing | On-demand delivery of computing services over the internet
Machine Learning | Field of AI that enables systems to learn from data
AI | Artificial Intelligence
Data Analytics | Process of examining data to draw conclusions
Big Data | Extremely large data sets analyzed to reveal patterns
Cybersecurity | Protection of internet-connected systems from digital attacks
DevOps | Software development and IT operations practices
Agile | Iterative approach to software development
Scrum | Framework for agile project management
NLP | Natural Language Processing
Frontend | Part of a website or application that users interact with
Backend | Server-side of a website or application
Full Stack | Developer proficient in both frontend and backend
Version Control | System that records changes to a file or set of files over time
Git | Distributed version control system in our case Github
Repository | Storage location for code, documents, or other assets
Compiler | Program that translates source code into executable code
Debugging | Process of finding and fixing errors in code
Algorithm | Set of rules or instructions to solve a problem
Framework | Reusable, standardized set of tools or libraries for software development
Library | Collection of pre-written code that can be used to perform common tasks
Microservices / Module | Architectural style that structures an application as a collection of services
Serverless Computing | Cloud execution model where the provider dynamically manages server allocation
Ollama | Tool for managing the LLMs github.com/ollama
Virtual Machine | Emulation of a computer system

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | Establish the core architectural groundwork for the project.
5 | Begin development in areas for future expansion.
6 | Enhance user value by metricization
7 | Preparing for Midproject review
8 | Enhance the system's modularity and refine metric implementation, including refactoring code.
9 | Enhancing accuracy of LLM return
10 | Advancing Usability and LLM response rsatistics
11 | Design and develop a custom LLM.
12 | Develop a Continuous Integration (CI) use case and demonstrate its value to users.
13 | Prepare for demo day

## Velocity Tracking
Sprint # | Story Points Planned | Story Points Realized
1
2 | 33 | 36
3 | 22 | 20
4 | 23 | 23
5 | 27 | 28
6 | 21 | 25
7 | 49 | 24
8 | 28 | 28
9 | 35 | 34
10 | 35 | 18
11 | 25 | 27
12 | 42 | 48
13 | 29 | 22
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Velocity chart
Sprint | Average Realized | Average Planned
1 | 27.75 | 30.75
2 | 27.75 | 30.75
3 | 27.75 | 30.75
4 | 27.75 | 30.75
5 | 27.75 | 30.75
6 | 27.75 | 30.75
7 | 27.75 | 30.75
8 | 27.75 | 30.75
9 | 27.75 | 30.75
10 | 27.75 | 30.75
11 | 27.75 | 30.75
12 | 27.75 | 30.75
13 | 27.75 | 30.75
14 | 27.75 | 30.75

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 136 | 136 | 132
Sprints
1 |  |  | 0 | 136 | 0 | 132
2 |  |  | 33 | 103 | 36 | 132
3 |  |  | 33 | 70 | 20 | 96
4 |  |  | 22 | 37 | 23 | 76
5 |  |  | 27 | 15 | 28 | 53
6 |  |  | 21 | -12 | 25 | 25
7 | [5 empty] | 0
8 | [5 empty] | 0
9 | [5 empty] | 0
10 | [5 empty] | 0
11 | [5 empty] | 0
12 | [5 empty] | 0
13 | [5 empty] | 0
14 | [5 empty] | 0
15 | [5 empty] | 0
Finish | [5 empty] | 0
Features
1
(none since we didnt meet with the IP yet)
2
|  | Write .py script to interact with the LLM 3 | 3 |  | 3
|  | Reaserch LLM 5 | 5 |  | 5
|  | Research Deepcoder/Phi4-Mini | 5 |  | 5
|  | Reaserch LLM 4 | 5 |  | 5
|  | Reaserch LLM 2 | 5 |  | 8
|  | Create initial Architecture Documentation | 2 |  | 2
|  | Reaserch LLM 1 | 5 |  | 3
|  | Write .py script to interact with the LLM 1 | 3 |  | 5
3
|  | Continue to Maintain the Architecture-Document | 3 |  | 3
|  | Write .py script to interact with the LLM 2 | 3 |  | 3
|  | Research Code Complexity | 5 |  | 5
|  | Create Python test cases | 3 |  | 1
|  | Start Bill of Material | 1 |  | 1
|  | Continue to Maintain Bill of Materials | 1 |  | 1
|  | Write .py script to interact with the LLM 5 | 3 |  | 3
|  | Write .py script to interact with the LLM 4 | 3 |  | 3
4
|  | Continue to Maintain Bill of Materials | 1 |  | 1
|  | Unify the python interface | 3 |  | 3
|  | initialize ReadMe | 2 |  | 1
|  | Research AI-Model Benchmark | 3 |  | 3
|  | Build the first Benchmarking tests | 3 |  | 3
|  | make CI-Pipeline | 5 |  | 8
|  | Continue to Maintain the Architecture-Document | 3 |  | 2
|  | Set up Branchmanagment | 3 |  | 2
5
|  | Add Modul Interface | 5 |  | 5
|  | Research Ollama | 5 |  | 3
|  | Test docker performance | 3 |  | 5
|  | Initialize API | 5 |  | 5
|  | Build process video | 3 |  | 3
|  | Initialize Frontend | 5 |  | 3
|  | Continue to Maintain Bill of Materials | 1 |  | 1
|  | Make metrics.py into its own modul |  |  | 3
6
|  | Write .py script to start docker containers | 3 |  | 3
|  | Show POs how the Project works | 3 |  | 2
|  | Research: Spell checker | 3 |  | 3
|  | Onboard small LLM | 1 |  | 1
|  | Frontend Make User enter prompt and source code | 5 |  | 8
|  | Module: Analyze context size | 3 |  | 5
|  | Connect API to Frontend | 3 |  | 3
Leftovers
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Burndown chart
Ideal Case | Real Case | Sprint | Planned progress
|  | 1 | 136 | 136
|  | 2 | 108.25 | 100
|  | 3 | 80.5 | 80
|  | 4 | 52.75 | 57
|  | 5 | 25 | 39
|  | 6 | -2.75
|  | 7 | -30.5
ca. 30 pro sprint

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  | estimation ca. 30 per sprint | 243 | 243
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
7 |  |  | 49 | 243 | 24 | 243
8 |  |  | 28 | 194 | 28 | 219
9 |  |  | 35 | 166 | 34 | 191
10 |  |  | 35 | 131 | 18 | 157
11 |  |  | 25 | 96 | 27 | 139
12 |  |  | 42 | 71 | 48 | 112
13 |  |  | 29 | 29 | 22 | 64
Features
7
|  | Module. Evaluate LLM performance | 3
|  | Extract Code from Input/Output | 3 |  | 2
|  | Research/Implement How to include whole project | 5 |  | 13
|  | Module: Code Complexity MCC | 5
|  | Set up Docker compose | 5 |  | 5
|  | Unify build process | 5
|  | Bill of Material | 1 |  | 1
|  | Architecture Document | 3 |  | 3
|  | Module CCC | 5
|  | Initialize user, (technical) design, and build/deploy documentation | 3
|  | Refactoring: unify payload to json | 5
|  | Module: CMT Code Complexity | 3
|  | Set prerequistists for Modulel | 3
8
|  | Fix: keep models | 2 |  | 2
|  | Refactoring: unify payload to json | 5 |  | 5
|  | Bug-Fix: Update Extract Code from Input/Output #128 | 1 |  | 1
|  | Module CCC | 5 |  | 5
|  | Module. Evaluate LLM performance | 3 |  | 5
|  | Unify build process | 5 |  | 3
|  | Onboard and Test new LLM | 2 |  | 2
|  | Module: Code Complexity MCC | 5 |  | 5
9
|  | Onboard and Test new LLM | 2 |  | 2
|  | Module: Add configurable outputs | 3 |  | 3
|  | Research: Befits of chaining methods | 3 |  | 3
|  | Test current models for consitency | 3 |  | 2
|  | Module: LLM testing of Code understandability, make LLM describe the code, let the same LLM (with no history) build the code from the description -> see if code passes the Unit tests. | 3 |  | 3
|  | Research: How to measure code coverage with tools | 3 |  | 3
|  | Frontend: make modules togglable in UI | 5
|  | Frontend: Diff viewer between original and tested source | 5 |  | 5
|  | Module: external research | 5 |  | 8
|  | Initialize user, (technical) design, and build/deploy documentation | 3 |  | 5
10
|  | Onboard and Test new LLM | 3 |  | 2
|  | Enable Output to Reinput for LLM | 5
|  | Module: Check output for code coverage of the tests | 5
|  | Clean up output code | 5
|  | Research: can we run the models in the CI | 3 |  | 3
|  | Module: Show dependency hierarchy of code by logic flow | 3 |  | 3
|  | Module: execute Tests | 5
|  | Research: How to train LLM | 3 |  | 5
|  | Research: How to finetune LLM | 3 |  | 5
11
|  | Research and Run first project on HPC | 3 |  | 5
|  | Module: execute Tests | 5 |  | 5
|  | Acquire Dataset: Unit-Tests | 3 |  | 3
|  | Acquire Dataset: Python-Tests | 3 |  | 3
|  | Use metrics to compare 1b, 3b, 7b and maybe 14b models | 8 |  | 8
|  | Set prerequistists for Modulel | 3 |  | 3
12
|  | Clean up output code | 5 |  | 5
|  | Onboard and Test new LLM | 2 |  | 2
|  | Module: Detect redundant/duplicate test cases | 3 |  | 3
|  | Enable Output to Reinput for LLM | 5 |  | 5
|  | Frontend: Upload .py files through the UI | 3 |  | 3
|  | Homework: Prepare Demo and create 3 Usecases | 2 |  | 2
|  | Homework: Create Demo Day slide | 3 |  | 5
|  | Homework: Create Demo Day video | 5 |  | 8
|  | Refactor: Readme files | 2 |  | 2
|  | Refactor: clean repo | 5 |  | 3
|  | Frontend: Display Outputs of Selected Modules | 3 |  | 5
|  | Onboard and Test new LLM | 2 |  | 3
|  | Acquire English-Dataset for LLM | 2 |  | 2
13
|  | Clean the wiki | 3 |  | 3
|  | Homework: Overwork the Bill of Materials | 3 |  | 3
|  | Homework: Overwork the Architectuer Document | 3 |  | 5
|  | {user¦design¦build}-documentation.pdf | 3 |  | 3
|  | Eveluate the performance of the models with and without the modules | 3 |  | 3
|  | Check Docker: streamline build process | 3
|  | Module: Check output for code coverage of the tests | 5
|  | Demoday Prep: Cheat sheet | 3 |  | 5
|  | (Module:) Output Exporter | 3

## Final Project Burndown chart
Sprint | Prediction
7 | 243
8 | 212.25
9 | 181.5
10 | 150.75
11 | 120
12 | 89.25
13 | 58.5
Note: only the current sprints are accurate | It is accurate for the final release

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done
1 | # Definition of Done - [ ] document the results of your research - [ ] note if the LLM works or not - [ ] add documentation to the LLM section of the wiki - [ ] link any sources you found, preferably scientific | Project builds, deploys, and tests successfully Project is improved compared to last release Sprint release notes have been written Wiki has been updated with new knowledge | Release passes accaptence test Functional and non functional requirements are met Requirements and Use cases are covered User documentation has been updated Design documentation has been updated
2 | # Definition of Done - [ ] Code is tested - [ ] Code is reviewed by a peer - [ ] Code is merged into dev (without breaking) - [ ] Code is Documented in the Wiki

## Documentation
Type | Link / reference
Wiki | https://github.com/amosproj/amos2025ss04-ai-driven-testing/wiki
Architecure | https://github.com/amosproj/amos2025ss04-ai-driven-testing/wiki/Architecture
Build and Deployment Guide | https://github.com/amosproj/amos2025ss04-ai-driven-testing/wiki/Build-and-Deployment-Guide
Top-Level Readme: | https://github.com/amosproj/amos2025ss04-ai-driven-testing
Overview for models | https://github.com/amosproj/amos2025ss04-ai-driven-testing/wiki/Comparison-of-1b,-3b,-7b-and-14b-models
Documentation (e.g Architecture) | https://github.com/amosproj/amos2025ss04-ai-driven-testing/tree/development/Documentation
Deliverables (e.g Homework) | https://github.com/amosproj/amos2025ss04-ai-driven-testing/tree/development/Deliverables

## Bill of Materials
| Name | Version | License | Comment
🧰 Main Tools
| Python | 3.13.2 | Python Software Foundation License Version 2 | For running the main script
| Docker | 28.1.1 | Apache License, Version 2.0 | Ollama enables running LLMs easily
| Ollama | 0.6.8 | MIT License
| conda | 25.5.0 | BSD-3 License | environment management
| conda-forge | 25.5.0 | BSD-3 License | Distribution channel
🤖 Used LLMs (via Ollama)
| StarCoder2 | starcoder2:3b | Apache License, Version 2.0 | Running StarCoder2 3B via Ollama
| Qwen2.5-coder | qwen2.5-coder:3b-instruct-q8_0 | Qwen Research License (3B Model only), Apache License 2.0 (others) | Running Qwen2.5-Coder via Ollama
| Mistral | mistral:7b-instruct-v0.3-q3_K_M | Apache License, Version 2.0 | Running Mistral via Ollama
| OpenHermes 2.5 | openhermes:v2.5 | Apache License, Version 2.0 | Running OpenHermes via Ollama
| Phi4-Mini | phi4-mini:3.8b-q4_K_M | MIT License | Running Phi4-Mini via Ollama
| Phi4-reasoning | phi4-reasoning:14b | MIT License | Running Phi4-reasoning via Ollama
| Tinyllama | tinyllama:1.1b | Apache License, Version 2.0 | Running Tinyllama via Ollama
| Qwen3 | qwen3:4b-q4_K_M | Apache License, Version 2.0 | Running Qwen3 via Ollama
| Smollm2 | smollm2:360m | Apache License, Version 2.0 | Running Smollm2 via Ollama
🛠️ Backend
| pytest | 8.3.1 | MIT License | used for unit‐tests
| docker | 7.1.0 | Apache License, Version 2.0
| requests | 2.32.3 | Apache License, Version 2.0
| tqdm | 4.67.1 | MIT License
| numpy | 1.22.0 | BSD License
| pandas | 1.3.0 | BSD License
| fastapi | 0.115.1 | MIT License
| uvicorn[standard] | 0.34.0 | BSD License
| transformers | 4.52.2 | Apache License, Version 2.0
| langchain | 0.3.25 | MIT License
| langchain_community | 0.3.24 | MIT License
| langchain-chroma | 0.2.4 | MIT License
| langchain_text_splitters | 0.3.8 | MIT License
| langchain_ollama | 0.3.24 | MIT License
| keybert | 0.9.0 | MIT License
| langchain | 0.9.0 | MIT License
| beautifulsoup4 | 4.13.4 | MIT License
| py2cfg | 1.0.5 | Apache License, Version 2.0
| mccabe | 0.7.0 | MIT License
| pydantic | 2.11.7 | MIT License
| staticfg | 0.9.5 | Apache License, Version 2.0
| Black | 25.1.0 | MIT License | Used for Code formatting
| flake8 | 7.0.0 | MIT License | Used for Linting
🎨 Frontend
| @emotion/react | 11.14.0 | MIT License
| @emotion/styled | 11.14.0 | MIT License
| @fontsource/roboto | 5.2.5 | MIT License
| @mui/icons-material | 7.1.0 | MIT License
| @mui/material | 7.1.0 | MIT License
| @testing-library/dom | 10.4.0 | MIT License
| @testing-library/jest-dom | 6.6.3 | MIT License
| @testing-library/react | 16.3.0 | MIT License
| @testing-library/user-event | 13.5.0 | MIT License
| @types/jest | 27.5.2 | MIT License
| @types/node | 16.18.126 | MIT License
| @types/react | 19.1.4 | MIT License
| @types/react-dom | 19.1.5 | MIT License
| fr | 1.2.2 | MIT License
| react | 19.1.0 | MIT License
| react-dom | 19.1.0 | MIT License
| react-dropzone | 14.3.8 | MIT License
| react-markdown | 10.1.0 | MIT License
| react-scripts | 5.0.1 | MIT License
| remark-gfm | 4.0.1 | MIT License
| typescript | 4.9.5 | Apache-2.0 License
| web-vitals | 2.1.4 | Apache-2.0 License

## Planning Poker
Last Name | First Name | Value
Brüggemann | Jonas | 5 | 5 | OK
Clicqué | Lennard | 5
Hasse | Lisabeth | 5
Heidkamp | Tessa | 5
Parameswaran | Biranavan | 5 | 0 | No size
Takale | Aditi Vishwas | 5 | 1 | Trivial size
|  |  | 2 | Small size
|  |  | 3 | Medium size
|  |  | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value